{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["重点项目","预备项目"],"not_rendered":{"external_links":2,"defined_names":6},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"重点项目","index":0,"n_rows":139,"n_cols":11,"rows_kept":139,"merged":[[0,0,0,1],[1,0,1,10],[2,0,2,8],[2,9,2,10],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,4,6],[3,7,4,7],[3,8,4,8],[3,9,4,9],[3,10,4,10]],"flags":["formulas_cached_only"]}
["附件1"]
["阳江市2019年重点建设项目计划表"]
[{"$nulls":9},"单位：万元"]
["序号","项目名称","建设性质","建设内容及规模","建设起止年限","总投资     ","至2018年底累计完成投资","2019年计划投资","2019年主要工程建设内容","责任\n单位","备注"]
[]
[null,"合计112项",{"$nulls":3},{"v":34263237.6,"d":"34263238"},13541933,2680000]
["一","基础设施工程（共41项）",{"$nulls":3},{"v":23701971.6,"d":"23701972"},10046780,1612000]
["（一）","交通运输工程（19项）",{"$nulls":3},6427007,535024,551000]
[null,"投产项目（1项）"]
[1,"怀集至阳江高速公路海陵岛大桥","投产","高速公路9.232公里","2016-2019",97500,65761,25000,"路面工程","市交通运输局","市属落户县（市、区）项目"]
[null,"续建项目（11项）"]
[2,"沈海高速公路开阳段扩建工程阳江段","续建","高速公路45.6公里","2018-2022",433091,80125,100000,"路基、桥涵工程","市交通运输局","市属落户县（市、区）项目"]
[3,"沈海高速公路阳茂段改扩建工程阳江段","续建","高速公路51.8公里","2018-2022",571000,42000,80000,"路基、桥涵工程","市交通运输局","市属落户县（市、区）项目"]
[4,"中阳高速公路阳春段","续建","高速公路42.2公里","2017-2020",740000,170550,150000,"路基、桥涵、隧道、管线迁改工程","市交通运输局","市属落户县（市、区）项目"]
[5,"广东滨海旅游公路阳江段（先行段）","续建","新建一级公路46.18公里，其中雅韶至山外东段9.98公里；山外东至海陵大堤段11.2公里；海陵大堤至溪头段25公里","2018-2022",611000,23390,30000,"征地拆迁、路基及桥涵工程","市交通运输局","市属落户县（市、区）项目"]
[6,"国道325线阳江市北惯至白沙段改线工程","续建","新建一级公路26.5公里","2017-2020",91755,60000,30000,"桥涵、路面工程","市公路局","市属落户县（市、区）项目"]
[7,"国道325线阳西县城过境公路工程","续建","一级公路11.7公里，其中市政配套路段长5.5公里","2017-2020",54531,21698,5000,"路基、路面、桥涵工程","阳西县政府","阳西县项目"]
[8,"省道S540线阳江雅韶至白沙段扩建工程","续建","一级公路17.8公里","2018-2020",136665,10000,30000,"路基、桥涵工程","市交通运输局","市属落户县（市、区）项目"]
[9,"省道S540线平冈至阳江港段改建工程","续建","一级公路8.4公里","2018-2020",31700,7800,10000,"路基、桥涵工程","市交通运输局","市属落户县（市、区）项目"]
[10,"省道S297线合山至大沟段公路","续建","新建一级公路18.8公里","2018-2020",30200,15700,8000,"路基、桥涵工程","阳东区政府","阳东区项目 "]
[11,"阳江港进港航道改造工程","续建","10万吨级航道19.924公里","2018-2020",94400,10000,30000,"航道疏浚","市交通运输局","市属落户县（市、区）项目"]
[12,"阳江港18#码头泊位建设工程","续建","建设1个10万吨级通用码头泊位","2018-2020",81000,28000,10000,"沉箱水下安装、码头陆域工程","阳江高新区管委会","阳江高新区项目 "]
[null,"新开工项目（7项）",null,null,"  "]
[13,"广州至湛江客运专线阳江段","新开工","高速铁路120公里","2019-2024",2400000,0,2000,"土建、路基、桥涵等工程","市发展改革\n局、市交通运输局","市属落户县（市、区）项目 "]
[14,"西部沿海高速阳江南联络线","新开工","高速公路28.37公里","2019-2022",625600,0,3000,"征地拆迁等前期工作","市交通运输局","市属落户县（市、区）项目 "]
[15,"国道G234线双捷桥至海陵大堤段扩建工程","新开工","一级公路33公里","2019-2021",67967,0,10000,"征地拆迁、路基、桥涵工程","市交通运输局","市属落户县（市、区）项目"]
[16,"国道G325线阳江市江城坪郊至轮水段新（改）建工程","新开工","新建一级公路24.848公里","2019-2020",75921,0,10000,"路基、桥涵工程","市公路局","市属落户县（市、区）项目"]
[17,"阳江港疏港公路","新开工","新建一级公路8.2公里","2019-2020",80610,0,6000,"路基、桥涵工程","市交通运输局","市属落户县（市、区）项目"]
[18,"阳江港22#码头泊位建设工程","新开工","建设1个5万吨级码头泊位","2019-2023",120000,0,5000,"陆域填筑","阳江高新区管委会","阳江高新区项目 "]
[19,"广东华厦阳西电厂配套码头扩建工程项目","新开工","扩建1个7万吨级卸煤泊位","2019-2020",84067,0,7000,"基槽开挖、构件预制、航道疏浚、设备购置等","阳西县政府","阳西县项目 "]
["（二）","能源保障工程（12项）",{"$nulls":3},16406202,9388519,930000]
[null,"投产项目（2项）"]
[20,"阳江核电厂工程","投产","6台108.6万千瓦级压水堆核电机组","2008-2019",8482211,7895697,300000,"6号机组实现并网","阳江核电有限公司","市属落户县（市、区）项目"]
[21,"阳西电厂二期#5、#6号机组工程","投产","2台装机容量1240兆瓦机组","2014-2019",903635,753404,50000,"6号机组调试投产","阳西县政府","市属落户县（市、区）项目"]
[null,"续建项目（7项）"]
[22,"阳江抽水蓄能电站","续建","装机容量240万千瓦，分近、远两期建设，近期建设规模120万千瓦","2015-2023",762738,197650,70000,"上下水库工程，厂房及水道系统工程","阳春市政府","市属落户县（市、区）项目"]
[23,"粤电阳江沙扒海上风电项目","续建","装机容量300兆瓦","2017-2020",599971,50673,60000,"海上升压站、陆上控制中心、风机基础工程；海上电缆采购等","阳西县政府","市属落户县（市、区）项目"]
[24,"三峡新能源阳西沙扒300兆瓦海上风电场项目","续建","装机容量300兆瓦","2017-2020",541982,91142,100000,"海缆建造、风机吊装、集控中心建安及海上升压站电气设备安装等","阳西县政府","市属落户县（市、区）项目"]
[25,"中广核阳江南鹏岛海上风电项目","续建","装机容量400兆瓦","2018-2020",700000,76560,80000,"海上升压站、陆上集控中心，完成首批风机并网发电","阳东区政府","市属落户县（市、区）项目"]
[26,"中节能阳江南鹏岛海上风电项目","续建","装机容量300兆瓦","2018-2020",578210,77821,100000,"集控中心、敷设海底电缆、建设海上升压站、风机基础及风机吊装","阳东区政府","市属落户县（市、区）项目"]
[27,"阳江市调峰储气库","续建","2座容量为16万立方米（年设计处理能力约为200万吨/年）的LNG储气库及相关配套设施","2018-2023",280000,15100,10000,"陆域形成工程","阳江高新区管委会","市属落户县（市、区）项目"]
[28,"阳江500千伏、220千\n伏、110千伏及以下配网工程","续建","500千伏电网工程、220千伏电网工程、110千伏电网工程","2015-2020",297810,230472,80000,"电网基建工程","阳江供电局","市属落户县（市、区）项目"]
[null,"新开工项目（3项）"]
[29,"明阳阳江沙扒300兆瓦科研示范项目","新开工","装机容量300兆瓦","2019-2020",585805,0,25000,"风机基础建设和风机吊装","阳西县政府","市属落户县（市、区）项目"]
[30,"三峡新能源阳西沙扒二期400兆瓦海上风电场项目","新开工","装机容量400兆瓦","2019-2021",761840,0,25000,"风机基础建设和风机吊装","阳西县政府","市属落户县（市、区）项目"]
[31,"三峡广东阳江阳西沙扒三、四、五期1000兆瓦海上风电场项目","新开工","装机容量1000兆瓦","2019-2021",1912000,0,30000,"土建、设备安装","阳西县政府","市属落户县（市、区）项目"]
["（三）","城建基础设施工程（10项）",{"$nulls":3},{"v":868762.6,"d":"868763"},123237,131000]
[null,"投产项目（3项）"]
[32,"金平路建设项目一期工程","投产","道路7.4公里，含桥梁、排水、照明、绿化及绿道等工程","2016-2019",78069,46000,8000,"桥梁工程、道路工程","阳江滨海新区管委会","阳江滨海新区项目"]
[33,"新阳路地下综合管廊及同步建设工程","投产","地下综合管廊1100米及配套市政道路、排水、电力、通讯、燃气等工程","2018-2019",18760,5000,5000,"地下管廊主体工程、安装工程及配套工程","阳江滨海新区管委会","阳江滨海新区项目"]
[34,"阳春市生活污水处理设施全市打包PPP模式建设项目","投产","河、松柏、石望等10个一般镇污水处理厂及配套管网，城区污水处理厂及配套管网工程","2017-2019",39800,15835,10000,"污水处理厂及管网建设","阳春市政府","阳春市项目"]
[null,"续建项目（4项）"]
[35,"阳江市四围涝区整治工程","续建","新建1座排涝泵站，设计排涝流量为70立方米/秒，总装机容量为4500千瓦","2018-2020",10200,1100,5000,"建设排涝泵站","市水务局","市属落户县（市、区）项目"]
[36,"阳江市市区市政基础设施建设项目 ","续建","站前路、石湾路、市区高压走廊升级改造、龙涛红丰区截污、生活垃圾转运站、市区公厕、长洲岛纵一路、沿江路、鸳鸯湖环湖二路、漠阳江东西河大桥、市区旧路（2017）、G325国道改线市政配套、共青湖公园及沿山路、森林公园二期、文化公园、振兴路下穿隧道和高速出入口道路等17项","2017-2021",144633,37806,25000,"道路、管道、绿化、路灯、交通设施等工程","市城市管理和综合执法局","市直项目"]
[37,"阳江市市区市政基础设施PPP项目 ","续建","金郊路、金山路、三环南路、四围大道二期和南浦大道三期、发财路、康泰北路、中洲大道扩\n建、三江中路、中洲大道延长线等10道路；老城区截污及排水管网改造、城北片区截污及排水管网改造等5个工程；三江岛中洲岛污水厂、城南污水处理厂二\n期、城北污水处理厂扩容提标等3个工程","2018-2021",238921,8575,30000,"道路、人行道、排水、绿化、路灯、交通设施等；污水管道及配套工程","市城市管理和综合执法局","市直项目"]
[38,"阳东PPP模式整区推进村镇污水处理建设项目","续建","城区和经济开发区污水厂已建部分提标改造，城区及各镇区新建污水管网181千米；全区225个新建农村污水设施；城区66公里市政道路雨污分流改造","2018-2020",{"v":78204.6,"d":"78205"},8921,15000,"污水处理设施、管网建设等","阳东区政府","阳东区项目 "]
[null,"新开工项目（3项）"]
[39,"阳江市大河水库引水工程","新开工","建设引水隧洞及水源地管理站；铺设DN2600输水管道和DN2000输水管道，全程约60.3千米","2019-2021",195000,0,20000,"征地拆迁、建设引水隧洞、铺设输水管道","市水务局","市属落户县（市、区）项目 "]
[40,"“两江四岸”景观设施升级改造项目GHI段","新开工","新江南路至三廉公园段长约5.6公里","2019-2020",20000,0,5000,"景观建设","市代建项目管理局","市直项目"]
[41,"阳西县整县推进镇村污水处理设施建设项目","新开工","新建污水处理厂0.885万吨/天，镇村新建521座农村小型污水处理设施及配套管网","2019-2020",45175,0,8000,"镇区污水厂及农村污水处理设施","阳西县政府","阳西县项目 "]
["二","产业工程（共59项）",{"$nulls":3},9852805,3116739,970000]
[null,"投产项目（10项）"]
[42,"明阳风机装备制造整机项目","投产","占地面积270亩，建设30条生产线，生产大型海上风电整机及配套产品，年产量300套","2017-2019",100000,63700,20000,"厂房装修、设备安装及调试","阳江高新区管委会","阳江高新区项目 "]
[43,"广青金属压延不锈钢深加工项目","投产","建设年产200万吨不锈钢深加工生产线及配套设施，承接广青科技200万吨不锈钢坯，生产不锈钢压延卷板","2016-2019",195000,180000,10000,"厂房装修、设备安装及调试","阳江高新区管委会","市属落户县（市、区）项目"]
[44,"卡夫亨氏阳江新建食品工厂项目","投产","占地面积233亩，建设厂房、仓库、饭堂、发酵区等","2018-2019",70000,35000,20000,"主体建筑施工，设备安装调试","阳西县政府","阳西县项目 "]
[45,"鼎华晟不锈钢门业制品项目","投产","占地面积23300平方米；建设厂房约15000平方米，建设两条生产线","2017-2019",20000,15000,5000,"建设第二条生产线","江城区政府","江城区项目 "]
[46,"广东新兴铸管有限公司二期项目 ","投产","建设一条年产20万吨球墨铸管生产线，产品铸管规格DN350～800","2018-2019",30000,0,25000,"厂房建设、设备安装","阳春市政府","阳春市项目"]
[47,"广东天下先钢结构有限公司钢结构生产项目","投产","建筑面积23000平方米，建设厂房、办公楼及生产线","2018-2019",11000,0,9000,"厂房建设、设备安装","阳春市政府","阳春市项目"]
[48,"江城史特牢金属紧固件项目","投产","占地面积19963平方米，生产8.8级以上标准的防松垫片、螺母、螺丝等金属紧固件","2018-2019",15000,0,15000,"厂房建设、设备安装","江城区政府","江城区项目 "]
[49,"广东必红实业公司建设项目（阳东）","投产","占地面积21000平方米，建设厂房、办公楼","2018-2019",15000,4300,10000,"厂房建设、设备安装","阳东区政府","阳东区项目 "]
[50,"阳江南信实业公司建设项目（阳东）","投产","占地面积24000平方米，主要建设厂房、办公楼","2018-2019",15000,4000,10000,"厂房建设、设备安装","阳东区政府","阳东区项目 "]
[51,"阳春产业转移工业园孵化中心","投产","用地面积32113平方米，总建筑面积47300平方米","2018-2019",14980,600,10000,"土建及安装工程","阳春市政府","阳春市项目"]
[null,"续建项目（24项）"]
[52,"珠海（阳江）产业转移工业园","续建","规划用地面积21.8平方公里，规划有福冈、临港和平东等三片区，建设园内基础设施","2006-2022",916540,358804,50000,"园区基础设施建设","阳江高新区管委会","阳江高新区项目 "]
[53,"珠海（阳江万象）产业转移工业园 ","续建","进行土地平整、园区基础设施、道路、管网工程等建设","2006-2020",170000,140067,10000,"园区基础设施建设","阳东区政府","阳东区项目 "]
[54,"中山火炬（阳西）产业转移工业园基础设施项目","续建","规划用地面积11000亩，进行用地平整、路网、排水排污等基础设施建设","2005-2020",210000,111487,8000,"园区基础设施建设","阳西县政府","阳西县项目 "]
[55,"高新区甬金金属科技公司68万吨冷轧项目","续建","规划用地面积400亩，生产不锈钢冷轧板，年产量达到30万吨以上","2018-2020",181000,6800,50000,"厂房及配套基础设施建设","阳江高新区管委会","阳江高新区项目 "]
[56,"高新区宏旺70万吨不锈钢冷轧板项目","续建","建造2条1450四连轧连退生产线，生产高品质不锈钢冷轧板70万吨/年；建设不锈钢剪切和表面精加工车间","2018-2020",150000,25000,50000,"建设车间及订购设备","阳江高新区管委会","阳江高新区项目 "]
[57,"阳江山河游艇制造基地建设项目（阳江港7#码头工程）","续建","建设集游艇研发、制造、销售、维修、应用示范及营运一体的新兴产业项目","2018-2020",38000,7400,8000,"吹填土工程、沉箱预\n制、沉箱水下安装","阳江高新区管委会","阳江高新区项目 "]
[58,"广东厨邦食品有限公司食品生产项目（阳西）","续建","占地面积951.47亩，年产100万吨系列调味品","2012-2020",150000,106380,8000,"建设三期天然油扩产项目","阳西县政府","阳西县项目 "]
[59,"高新区和鲜食品科技产业园项目","续建","建设食品生产线，包含酿蒜、饮料、食品、复合香辛料、豆豉、鱼加工产品、速冻包子等","2018-2023",300000,40600,20000,"建设香辛料生产线以及订购安装相关设备","阳江高新区管委会","阳江高新区项目 "]
[60,"阳西美味鲜食品有限公司食品生产项目","续建","项目建筑面积200000平方米，建设黄酒储罐区、醋车间、食用油车间、料酒车间等单体","2017-2020",162533,23352,8000,"建设厂房、设备生产线以及辅助性生产设施","阳西县政府","阳西县项目 "]
[61,"江城景田纯净水项目","续建","占地面积8万平方米，建设三条德国克朗斯公司纯净水生产线","2018-2020",30000,3500,10000,"建设厂房及配套用房","江城区政府","江城区项目 "]
[62,"阳西领尊能源化工有限责任公司年处理5万吨废矿物油项目","续建","占地面积350亩，以废矿物油为原料经高度设备理化和化学技术处理后生产溶剂油、燃料油、润滑基础油等产品","2018-2020",22334,8000,10000,"建设厂房","阳西县政府","阳西县项目 "]
[63,"三威汽车零配件项目","续建","占地面积160000平方米，建设厂房及配套设施，生产涂装处理工艺汽车零配件电镀及组装等","2015-2021",180000,71350,10000,"建设汽车配件注塑项目及第二条龙门电镀生产线","江城区政府","江城区项目 "]
[64,"澳澜高分子硅胶制品项目","续建","占地面积6万平方米，建设厂\n房、办公、研发、检测中心、配送中心及商务等服务中心","2016-2020",30000,16363,10000,"建设厂房及配套设施","江城区政府","江城区项目 "]
[65,"江城港富硅胶制品项目","续建","占地面积22900平方米，建设厂房及配套用房","2018-2020",10569,1569,5000,"建设厂房及配套设施","江城区政府","江城区项目 "]
[66,"江城鸿德硅胶生产项目","续建","占地面积13000平方米，建设厂房及配套用房","2018-2020",10000,1000,5000,"建设厂房及配套设施","江城区政府","江城区项目 "]
[67,"阳江滨海中央商务区项目","续建","占地面积1099亩，建设办公楼\n群、LOFT创意办公区、商业综合体、商业区、品牌酒店或酒店式公寓、游艇会俱乐部及配套设施、高端住宅小区","2018-2024",1410000,203454,150000,"住宅楼、商业办公楼主体工程","阳江滨海新区管委会","阳江滨海新区项目"]
[68,"阳江保利海陵十里银滩","续建","涵盖住宅、公寓、五星级酒店、大型体育文化公园，总建筑面积100万平方米","2010-2020",600000,552362,7000,"主体及修饰工程","海陵试验区管委会","海陵试验区项目 "]
[69,"保利顺峰北洛秘境","续建","建设悦榕庄酒店等旅游设施","2015-2025",600000,166830,30000,"建设悦榕庄酒店","海陵试验区管委会","海陵试验区项目 "]
[70,"阳江恒大御景湾","续建","占地面积1198131平方米，建设酒店、住宅等旅游综合服务设施和公用配套设施","2012-2020",600000,298236,10000,"建设温泉小镇、酒店、酒吧街、文化街等","海陵试验区管委会","海陵试验区项目 "]
[71,"万豪海陵湾一号","续建","占地面积600多亩，建设万豪酒店、万怡酒店、产权式酒店及高层公寓","2015-2020",300000,96600,20000,"主体及修饰工程","海陵试验区管委会","海陵试验区项目 "]
[72,"敏捷·黄金海岸","续建","占地面积200万平方米，建设酒店、公寓等旅游设施","2012-2020",510000,473225,20000,"建设海玥湾、喜来登酒店","海陵试验区管委会","海陵试验区项目 "]
[73,"阳江星港汇","续建","项目占地面积42万平方米，建设商业中心及住宅建筑","2018-2022",130000,71500,15000,"建设商业中心、高层住宅楼","阳东区政府","阳东区项目 "]
[74,"苏航农业科技“三产合一”项目","续建","建设6000亩种植大棚","2018-2020",40000,15000,15000,"建设3000亩种植大棚","江城区政府","江城区项目 "]
[75,"闸坡中心渔港升级改造工程","续建","护岸及环港道路改造，新建高\n桩、重力及渔业码头，扩建南北防波堤、南防波堤观光区，洲仔峡改堤建桥及配套设施等","2016-2020",25849,15260,5000,"南北防波堤扩建及附属工程","海陵试验区管委会","海陵试验区项目 "]
[null,"新开工项目（25项）"]
[76,"高新区永贤科技不锈钢深加工产业园项目","新开工","建设不锈钢专业产业园，主要集聚中等以上规模不锈钢深加工及相关配套企业","2019-2021",100000,0,10000,"建设厂房及辅助设施","阳江高新区管委会","阳江高新区项目 "]
[77,"高新区开宝新材料年产20万吨不锈钢精加工项目","新开工","生产不锈钢彩色板、磨砂板、压花板、无指纹板为主的不锈钢装饰板、家电面板、深加工原料板材等产品","2019-2020",30000,0,10000,"建设厂房及辅助设施","阳江高新区管委会","阳江高新区项目 "]
[78,"龙马集团阳江高端装备制造基地项目","新开工","规划用地面积1200亩，生产铸\n铁、铸钢、起重器、压力容器、风电塔架、港口机械、汽车零部件","2019-2022",1000000,0,70000,"建设铸铁、铸钢、起重器、压力容器、风电塔架、港口机械生产线","阳江高新区管委会","市属落户县（市、区）"]
[79,"中车电机制造项目","新开工","建设生产厂房，建成年产150台6.0兆瓦半直驱永磁风力发电机定子和套装生产线","2019-2020",100000,0,15000,"建设厂房及配套设施","阳江高新区管委会","阳江高新区项目 "]
[80,"宁波东方海上电缆制造项目","新开工","建设海上风电装备制造及运维基地，主要建设海上电缆","2019-2021",100000,0,10000,"建设车间，设备订购、调试","阳江高新区管委会","阳江高新区项目 "]
[81,"金风科技风机制造项目","新开工","建设海上风电整机及配套零部件生产基地、大数据中心、智能运维基地、风电智慧能源基地、培训机构等","2019-2020",150000,0,25000,"建设厂房、办公楼等","阳江高新区管委会","阳江高新区项目 "]
[82,"广东鉴衡海上风电装备检测认证与技术创新基地","新开工","建设承载基础、平台与地轨、厂房、吊装及测试设备等，建设风电装备认证中心、装备实验室等","2019-2021",35000,0,5000,"建设厂房、承载平台、办公楼及采购测试设备","阳江高新区管委会","阳江高新区项目 "]
[83,"英普奇点道具制造与模特生产项目","新开工","规划用地面积32亩，主要进行道具制造与模特生产","2019-2020",11000,0,5000,"建设车间，订购设备","阳江高新区管委会","阳江高新区项目 "]
[84,"阳西广味源调味品项目","新开工","占地181亩，建设酱油生产车间","2019-2021",80000,0,10000,"建设厂房","阳西县政府","阳西县项目 "]
[85,"阳西致美斋调味品项目","新开工","计划用地202亩，建设厂房、仓库办公楼、发酵区等","2019-2022",140000,0,10000,"建设厂房","阳西县政府","阳西县项目 "]
[86,"阳西加美味调味品项目","新开工","计划用地200亩，建设厂房、仓库、办公楼、发酵区等","2019-2021",68000,0,8000,"建设厂房","阳西县政府","阳西县项目 "]
[87,"阳西厨邦调味品生产项目","新开工","计划用地500亩，建设厂房、仓库、办公楼、发酵区等","2019-2021",300000,0,10000,"建设厂房","阳西县政府","阳西县项目 "]
[88,"阳西金鸿纸品包装项目","新开工","计划用地150亩，建设厂房、仓库、办公楼、宿舍等","2019-2022",72000,0,8000,"建设厂房","阳西县政府","阳西县项目 "]
[89,"阳西建铧玻璃瓶生产项目","新开工","计划用地150亩，建设厂房、窑炉、仓库、办公楼等","2019-2020",70000,0,8000,"建设厂房","阳西县政府","阳西县项目 "]
[90,"阳西功成塑料生产项目","新开工","占地95.8亩，主要为园区食品企业提供产业配套","2019-2021",38000,0,8000,"建设厂房","阳西县政府","阳西县项目 "]
[91,"江城农海产品仓储物流园项目","新开工","占地面积23300平方米，建设农产品交易市场、仓储物流","2019-2022",105000,0,5000,"建设农产品、海产品交易市场","江城区政府","江城区项目 "]
[92,"张小泉阳江刀剪智能制造中心项目","新开工","占地面积约86000平方米，建设刀剪车间、仓库、研发中心、检测中心、综合办公楼等","2019-2020",32000,0,5000,"建设厂房及配套设施","江城区政府","江城区项目 "]
[93,"广东省粤钢新材料科技公司建设项目","新开工","占地面积40000平方米，建设厂房、办公楼，主要产品为紧固件","2019-2020",30000,0,10000,"厂房建设、设备安装","阳东区政府","阳东区项目 "]
[94,"广东铭泽脚轮工业公司建设项目","新开工","占地面积24000平方米，建设厂房、办公楼，主要产品为五金制品","2019-2020",20000,0,10000,"厂房建设、设备安装","阳东区政府","阳东区项目 "]
[95,"阳江新特体育科技用品公司建设项目","新开工","占地面积24000平方米，建设厂房、办公楼，主要产品为体育用品","2019-2020",20000,0,10000,"厂房建设、设备安装","阳东区政府","阳东区项目 "]
[96,"阳春精装照明有限公司LED灯饰照明生产项目","新开工","占地面积20025平方米，建设厂房、办公楼及生产线等","2019-2020",23000,0,10000,"建设厂房、生产线","阳春市政府","阳春市项目 "]
[97,"阳春传祺照明有限公司LED灯饰照明生产项目","新开工","占地面积13734平方米，建设厂房、办公楼及生产线等","2019-2020",21000,0,10000,"建设厂房、生产线","阳春市政府","阳春市项目 "]
[98,"阳春皇玛电器实业有限公司LED五金生产项目","新开工","占地面积16338平方米，建设厂房、办公楼及生产线等","2019-2020",15000,0,10000,"建设厂房、生产线","阳春市政府","阳春市项目 "]
[99,"阳春利视界光电科技有限公司LED照明电器生产项目","新开工","占地面积16274平方米，建设厂房、办公楼及生产线等","2019-2020",15000,0,10000,"建设厂房、生产线","阳春市政府","阳春市项目 "]
[100,"江城宝信奔驰4S店项目","新开工","占地24000平方米，建设汽车交易中心、检测中心等","2019-2020",15000,0,10000,"建设汽车销售中心、检测中心","江城区政府","江城区项目 "]
["三","民生工程（共12项）",{"$nulls":3},708461,378414,98000]
[null,"投产项目（6项）"]
[101,"阳江市妇幼保健院新\n院、中医院二期广场地下人防工程","投产","妇幼保健院建筑面积5621平方米；中医院二期建筑面积8160平方米。抗力等级为核6级常6级，进行土建、装饰及配套工程","2017-2019",9700,1200,6000,"建设人防地下室及配套工程","市人民防空办公室","市直项目"]
[102,"阳西县儒洞镇中心卫生院升级迁建项目（阳西县第二人民医院）","投产","占地面积4300平方米，建设门诊住院大楼、行政大楼及附属配套设施","2017-2019",18000,5963,10000,"装修及设备安装工程","阳西县政府","阳西县项目 "]
[103,"阳西县妇幼保健院（阳西县计划生育服务中心）迁建项目","投产","规划用地面积15876平方米，建设1幢9层高建筑物及绿化、路\n灯、排水排污等附属设施","2018-2019",7800,2634,4000,"主体、装修及设备安装工程","阳西县政府","阳西县项目 "]
[104,"阳春市春湾中心卫生院升级建设项目","投产","总建筑面积30489平方米，建设门急诊大楼、住院大楼、后勤楼及配套设施","2017-2019",18000,8544,9000,"主体、安装及装饰工程","阳春市政府","阳春市项目"]
[105,"阳春市人民医院新住院大楼建设项目","投产","占地面积1873平方米，医疗设备采购、装修和信息化建设","2018-2019",14985,6300,6000,"主体、安装及装饰工程","阳春市政府","阳春市项目"]
[106,"阳春市公共卫生医院建设项目","投产","建设精神病住院楼、传染病住院楼及配套设施","2017-2019",15000,6000,8000,"主体、装修及设备安装工程","阳春市政府","阳春市项目"]
[null,"续建项目（4项）"]
[107,"阳江市中医医院二期工程","续建","占地面积12373平方米，包括综合楼、住院楼、裙房、二层连\n廊、风雨连廊及垃圾站等","2018-2021",24500,301,3000,"主体工程","市卫生健康局","市直项目 "]
[108,"阳东区人民医院住院综合楼","续建","建设住院综合楼，总建筑面积29700平方米","2018-2020",13000,762,5000,"主体工程","阳东区政府","阳东区项目 "]
[109,"阳江市城南公共租赁住房建设项目一期工程","续建","建设512套公租房和基础配套设施，总建筑面积33000平方米","2018-2020",9476,710,3000,"主体工程","市住房和城乡建设局","市直项目"]
[110,"阳西县旧城区改造建设项目","续建","用地面积2265亩，包括征地补偿及房屋拆迁安置工作，太平小学扩建工程、道路、桥梁工程建设和商业开发","2013-2023",500000,346000,25000,"市政道路建设、学校建设、商业开发","阳西县政府","阳西县项目 "]
[null,"新开工项目（2项）"]
[111,"阳江市档案馆、方志\n馆、党史馆（三馆合一）项目","新开工","规划建筑面积12800平方米，建设档案馆、方志馆、党史馆","2019-2020",8000,0,4000,"主体工程","市档案局","市直项目"]
[112,"华南师范大学附属阳春学校","新开工","建设学校办公楼、宿舍、体育馆等","2019-2020",70000,0,15000,"主体工程","阳春市政府","阳春市项目"]

{"sheet":"预备项目","index":1,"n_rows":75,"n_cols":7,"rows_kept":75,"merged":[[0,0,0,1],[1,0,1,6],[2,5,2,6]],"flags":["formulas_cached_only"]}
["附件2"]
["阳江市2019年重点建设前期预备项目计划表"]
[{"$nulls":5},"单位：万元"]
["序号","项目名称","建设内容及规模","总投资","2019年开展的前期工作内容","责任单位","备注"]
[null,"合计64项",null,27120378]
["一","基础设施工程（44项）",null,19153016]
["（一）","交通运输工程（17项）",null,3555745]
[1,"中山至茂名高速（粤桂界）阳春至高州段","高速公路55公里",800000,"规划选址、用地预审、用地报批、环评等","市交通运输\n局、阳春市政府","市属落户县（市、区）项目 "]
[2,"阳江市快速公共交通1号线一期、海陵岛支线工程","轻轨全长53.4公里",822000,"规划选址、用地预审、用地报批、环评等","市交通运输局","市属落户县（市、区）项目 "]
[3,"阳江港疏港铁路高新区至丰头段","按国铁II级标准、非电气化单线铁路建设，线路全长21公里",150000,"规划选址、用地预审、用地报批、环评等","市交通运输局","市属落户县（市、区）项目 "]
[4,"国道G325线阳春轮水至马水新风段新（改）建工程","一级公路20.523公里",61144,"用地预审、立项报批等前期工作","市公路局","市属落户县（市、区）项目 "]
[5,"国道G325线阳春潭水至长塘段","一级公路33.6公里",21847,"可研等前期工作","市公路局","市属落户县（市、区）项目 "]
[6,"省道S278线织篢至溪头段一级公路改建工程","一级公路21.3公里",106219,"规划选址、用地预审、可行性研究报告、用地报批、环评、征地拆迁等","阳西县政府","阳西县项目 "]
[7,"省道S541线阳西县城至上洋段公路改建工程","一级公路24.941公里",117198,"规划选址、用地预审、可行性研究报告、用地报批、环评、征地拆迁等","阳西县政府","阳西县项目 "]
[8,"省道S278线塘口至织篢段公路改建工程","一级公路6.315公里",31876,"规划选址、用地预审、可行性研究报告、用地报批、环评、征地拆迁等","阳西县政府","阳西县项目 "]
[9,"广东滨海旅游公路海陵岛支线","含海陵岛支线南海I号立交桥工程、海陵岛支线华山隧道工程、海陵岛支线环岛路（岛东线）工程",63365,"立项、环评、设计等前期工作","海陵试验区管委会","海陵试验区项目"]
[10,"阳江港丰头作业区1-12号码头泊位工程","12个5万-10万吨级码头泊位",960000,"规划选址、用海审批、环评等","市交通运输局","市属落户县（市、区）项目 "]
[11,"阳江港15#码头泊位建设工程","建设1个5万吨级、水工预留10万吨级通用码头泊位",40000,"《海域使用权证》报批等前期工作","阳江高新区管委会","阳江高新区项目"]
[12,"阳江港16#码头泊位建设工程","建设1个5万吨级、水工预留10万吨级通用码头泊位",40000,"《海域使用权证》报批等前期工作","阳江高新区管委会","阳江高新区项目"]
[13,"阳江港17#码头泊位建设工程","建设1个5万吨级、水工预留10万吨级通用码头泊位",40000,"《海域使用权证》报批等前期工作","阳江高新区管委会","阳江高新区项目"]
[14,"阳江港19#码头泊位建设工程","建设1个10万吨级多用途码头泊位",60000,"《海域使用权证》报批等前期工作","阳江高新区管委会","阳江高新区项目"]
[15,"阳江港J13-J14#泊位工程","建设1000-3000吨级多用途泊位2个",23000,"规划选址、用地及用海预审、可行性研究报告、用地报批等前期工作","市交通投资集团有限公司","市属落户县（市、区）项目 "]
[16,"阳江港20-21#通用码头","建设2个10万吨级通用码头",130096,"规划选址、用地及用海预审、可行性研究报告、用地报批等前期工作","市交通投资集团有限公司","市属落户县（市、区）项目 "]
[17,"阳江港25-26#泊位工程","拟建设5万吨级石油化工泊位2个",89000,"用海预审、环评、可行性研究报告等前期工作","市交通投资集团有限公司","市属落户县（市、区）项目 "]
["（二）","能源保障工程（20项）",null,15036786]
[18,"粤电阳江青洲一海上风电场项目","装机容量为400兆瓦",851836,"用海预审、用地预审等前期工作","阳西县政府","市属落户县（市、区）项目 "]
[19,"粤电阳江青洲二海上风电场项目","装机容量为600兆瓦",1310792,"用海预审、用地预审等前期工作","阳西县政府","市属落户县（市、区）项目 "]
[20,"华电阳江青洲三海上风电项目","装机容量为500兆瓦",900000,"用海预审、环评等前期工作","阳西县政府","市属落户县（市、区）项目 "]
[21,"明阳阳江青洲四海上风电场项目","装机容量为500兆瓦",1000000,"环评、规划许可、征地、用地报批等前期工作","阳西县政府","市属落户县（市、区）项目 "]
[22,"三峡阳江青洲五海上风电场项目","装机容量为1000兆瓦",2000000,"用海预审、环评、施工许可等前期工作","阳西县政府","市属落户县（市、区）项目 "]
[23,"三峡阳江青洲六海上风电场项目","装机容量为1000兆瓦",2000000,"用海预审、环评、施工许可等前期工作","阳西县政府","市属落户县（市、区）项目 "]
[24,"三峡阳江青洲七海上风电场项目","装机容量为1000兆瓦",2000000,"用海预审、环评、施工许可等前期工作","阳西县政府","市属落户县（市、区）项目 "]
[25,"中广核阳江帆石一海上风电场项目","装机容量为1000兆瓦",2000000,"用海预审、环评、施工许可等前期工作","阳东区政府","市属落户县（市、区）项目 "]
[26,"中广核阳江帆石二海上风电场项目","装机容量为1000兆瓦",2000000,"用海预审、环评、施工许可等前期工作","阳东区政府","市属落户县（市、区）项目 "]
[27,"阳春市相电新能源风电项目","装机容量为100兆瓦",105000,"各项支持性文件申报核准","阳春市政府","市属落户县（市、区）项目 "]
[28,"阳春市仙家垌风电场49.5兆瓦工程项目","装机容量为49.5兆瓦",43900,"征地放线、道路工程建设","阳春市政府","市属落户县（市、区）项目 "]
[29,"华能阳江东平风电场扩建项目","装机容量为30兆瓦",23458,"完成所有前期手续，道路及风机基础施工","阳东区政府","市属落户县（市、区）项目 "]
[30,"国华阳东大沟风电场","装机容量为47.5兆瓦",38291,"可行性研究报告、规划选址、用地用林报批、环评、规划许可等","阳东区政府","市属落户县（市、区）项目 "]
[31,"阳东大合风电场","装机容量为50兆瓦",45000,"列入省陆上风电发展规划及开展相关前期工作","阳东区政府","市属落户县（市、区）项目 "]
[32,"阳江高新区燃气冷热电联供电厂","建设2台6F级机组，预留扩建2台9F级机组",300000,"各项专题研究及项目核准","阳江高新区管委会","市属落户县（市、区）项目 "]
[33,"阳江500千伏线路和接入系统工程","建设500千伏芷寮至回隆线路工程（阳江段）、博贺电厂接入系统工程（阳江段）、阳西电厂#5、#6机组接入系统工程（含开关站）、抽水蓄能电站接入系统工程",201267,"项目用地预审、规划选址、环评、稳评、穿越水源保护区、穿越生态严控区、项目核准等前期工作","阳江供电局","市属落户县（市、区）项目 "]
[34,"阳江220千伏输变电和接入系统工程","建设220千伏春城Ⅱ输变电工程、城南输变电工程",78000,"规划选址、可研编制、环评、用地预审、土地规划调整、项目核准等前期工作","阳江供电局","市属落户县（市、区）项目 "]
[35,"阳江110千伏输变电、网架完善和接入系统工程","建设110千伏联安输变电工程、高新输变电工程、程村输变电工程、大八输变电工程、红丰输变电工程、阳春成瑞风电场接入系统工程",31742,"项目可研编制、用地预审、环评、水保、穿越生态严控区、项目核准等前期工作","阳江供电局","市属落户县（市、区）项目 "]
[36,"海陵区海鸿银滩分布式能源站","装机容量100兆瓦",86000,"完成土地征收手续、完成控规等前期工作","海陵试验区管委会","市属落户县（市、区）项目 "]
[37,"阳西综合能源利用与服务项目（分布式能源）","建设4座天然气分布式泛能站、1个地源热泵系统、园区配电网及园区屋面光伏项目",21500,"规划选址、用地预审、用地报批、环评等前期工作","阳西县政府","市属落户县（市、区）项目 "]
["（三）","城建等基础设施工程（7项）",null,560485]
[38,"阳江市漠阳江出海口综合整治工程","建设堤防加固升级工程，水系连通、水生态修复、水环境整治工程、涝区整治工程",338768,"项目初步设计及相关专题报告的编制和审批工作","市水务局","市属落户县（市、区）项目 "]
[39,"三江岛滨江公园","绿道、休闲亭台、绿化、照明等，用地规模66万平方米",15000,"立项、规划、勘察设计等前期工作","市城市管理和综合执法局","市直项目"]
[40,"江城对岸一级渔港及配套设施项目","新建码头、疏浚航道港池；建设吉鱼岛护坡、引堤、桥梁、吉鱼岛道路及配套基础设施",51253,"征地等相关前期工作","江城区政府","江城区项目"]
[41,"江城银岭科技产业园生活配套、东侧扩展区基础设施一期项目","生活配套设施建设公寓、幼儿园、市场、商铺、广场等；基础设施一期建设市政附属排水渠、道路、雨污水管道、路灯等配套",59766,"项目立项、设计、招标等前期工作","江城区政府","江城区项目"]
[42,"阳西县城东片区路网建设工程","建设环城大道，方正路，陶然路、排水排污、照明、绿化、交通设施等工程",37155,"项目立项、设计、招标等前期工作","阳西县政府","阳西县项目 "]
[43,"滨海新区竹洲大桥等市政基础设施项目","建设竹洲大桥、竹洲岛公园、南浦南路、环岛西路等基础设施项目",48200,"规划设计等前期工作","阳江滨海新区管委会","阳江滨海新区项目"]
[44,"阳江滨海生态公园一期项目","项目占地总面积约2000亩，主要规划建设滨海景观、游乐设施及道路等配套的服务设施",10343,"项目用地、用海及设计等前期工作","阳江滨海新区管委会","阳江滨海新区项目"]
["二","产业工程（14项）",null,7885073]
[45,"阳春废钢综合利用短流程炼钢（特钢）项目","项目总用地1000亩，建设电炉炼钢、轧钢（特钢）及相关辅助设施等",320000,"产能迁入、规划选址、用地预审、环评等前期工作","阳春市政府","阳春市项目"]
[46,"江城中民筑友装配式成套住宅项目","该项目占地面积约10.5万平方米，建筑面积50420平方米，主要生产PC构件",50073,"项目环评、报建等相关前期工作","江城区政府","江城区项目"]
[47,"广物汽贸城项目","总面积84000平方米，建设4S店、综合展厅、汽配市场、二手车市场、研发中心、新能源汽车中心、汽车主题酒店等",30000,"征地、规划报建等前期工作","江城区政府","江城区项目"]
[48,"金银湖旅游度假区","总体规划面积4415亩，拟开发生态观光、陆上游乐场、水上游乐、五星级酒店、旅游度假别墅、特色餐饮、自驾游基地等旅游项目",300000,"征地、规划报建等前期工作","阳春市政府","阳春市项目"]
[49,"阳春圆梦廊桥博览景区","拟修建十二座廊桥、一座博物馆，总建筑面积约 22.5 万平方米，建设观光、休闲、购物等综合体项目",225000,"立项、设计等前期工作","阳春市政府","阳春市项目"]
[50,"阳西县家具建材市场项目","新建家具建材市场15万平方米",80000,"规划选址、用地预审、用地报批、环评等前期工作","阳西县政府","阳西县项目 "]
[51,"阳西月亮湾滨海风情度假岛项目","项目规划用地7000亩，主要建设现代花海农田、园林式五星级酒店、温泉度假区、海上乐园、高层酒店服务公寓、人工海岛等",500000,"项目规划设计、可研论证等前期工作","阳西县政府","阳西县项目 "]
[52,"阳西蓝袍湾旅游综合体项目","项目规划面积1.5万亩，建设用地约3000亩，拟建设旅游、休闲、度假、餐饮等设施",1000000,"项目规划设计、可研论证等前期工作","阳西县政府","阳西县项目 "]
[53,"阳西白沙湾旅游综合体项目","项目拟规划面积10000亩，建设用地约2000亩，拟建设旅游、休闲、度\n假、餐饮等设施",500000,"项目规划设计、可研论证等前期工作","阳西县政府","阳西县项目 "]
[54,"阳西龙溪森林温泉王国项目","总面积约4800亩，建设温泉度假酒\n店、温泉文化及游乐设施、田园森林游乐设施、登山径、丛林民宿以及其他景观配套、旅居设施",600000,"项目规划设计、可研论证等前期工作","阳西县政府","阳西县项目 "]
[55,"阳西儒洞温泉度假区项目","建设温泉配套设施、服务商业设施、酒店娱乐设施等",50000,"项目规划设计等前期工作","阳西县政府","阳西县项目 "]
[56,"海陵山河文化产业示范基地","总用地面积398380平方米，建筑面积304274平方米，建设文化娱乐项目、广场、道路、社会停车场等",450000,"总体规划设计、勘测、征地拆迁等前期工作","海陵试验区管委会","海陵试验区项目 "]
[57,"恒大-华谊兄弟（阳江）电影城项目","规划用地约3400亩，建设电影小镇、文化旅游、文化展示于一体，辅以星级酒店、商务会议、休闲体育等功能配套的海上丝绸之路文化旅游项目",3750000,"征地拆迁等前期工作","阳江滨海新区管委会","阳江滨海新区项目"]
[58,"阳江市文化创意产业园","位于江城区原阳江渔船厂，占地面积8.5万平方米，建设文化旅游产业园",30000,"可行性研究报告、招商洽谈等前期工作","市文化广电旅游体育局","市属落户县（市、区）项目 "]
["三","民生工程（6项）",null,82289]
[59,"阳江市城南公共租赁住房建设项目二期工程","建设5幢住宅楼共688套公租房和基础配套设施，总建筑面积4.9万平方米",14139,"建设工程规划许可证、施工图审\n核、抗震、防雷、工程施工招标、施工许可等前期工作","市住房城乡建设局","市属落户县（市、区）项目 "]
[60,"广东省水下文化遗产保护中心","建设广东省水下文化遗产保护中心项目，总建筑面积为25190平方米",35000,"规划选址、用地预审、用地报批、环评等前期工作","市文化广电旅游体育局","市属落户县（市、区）项目 "]
[61,"阳江市教师发展中心","总用地面积30亩，建设2栋综合楼和1栋宿舍楼。",8000,"规划选址、立项、设计等前期工作","市教育局","市直项目"]
[62,"阳西县中等职业技术学校建设项目","占地面积100亩，建设教学楼、图书楼、实训楼、学生宿舍楼等",8950,"项目选址及立项，办理工程前期报建手续","阳西县政府","阳西县项目 "]
[63,"阳西县教师发展中心","用地50亩，建设教学楼、科学楼、综合楼等",8000,"项目选址及立项，办理工程前期报建手续","阳西县政府","阳西县项目 "]
[64,"阳西县第三小学建设项目","总用地面积47818平方米，建设教学综合楼、食堂、室外运动场等",8200,"项目选址及立项，办理工程前期报建手续","阳西县政府","阳西县项目 "]